## Plan
UAT Prep Activities
Sl. | Category | Description | Owner | Start | End | Duration | Predecessor | Status | Remarks
1 | Plan | Initialise UAT prep | Rama Man | 2021-01-11 | 2021-01-11 | 0h |  | In Progress
2 |  | User Readiness
2.1 | User | Identify users and roles for testing | Tom Ban | 2021-01-11 | 2021-01-14 | 8h |  | Closed
2.2 | User | Create ticket to create / change users in UAT | Tom Ban | 2021-01-14 | 2021-01-14 | 1h | 2.1, | Open
2.3 | User | Communicate UAT plan - schedule, users, resolvers, and communication | Tom Ban | 2021-01-15 | 2021-01-15 | 1h |  | Open
2.4 | User | Provide application familiarisation to new users | Tom Ban | 2021-01-18 | 2021-01-20 | 24h |  | Open
2.5 | User | Train users on testing, defect management process & tools | Val Kilmer | 2021-01-22 | 2021-01-22 | 1h |  | Open
2.6 | User | Organise defect management meetings | Val Kilmer | 2021-01-21 | 2021-01-21 |  | 2.3, | Open
2.8 | User | Validate application login | Tom Ban | 2021-01-29 | 2021-01-29 | 1h | 6, | Open
2.7 | User | Communicate user/passwords to individual users | Tom Ban | 2021-01-29 | 2021-01-29 | 1h | 6, | Open
2.9 | User | Send communication plan to initiate UAT | Tom Ban | 2021-01-29 | 2021-01-29 | 1h | 7.1, 5.1 | Open
3 |  | Salesforce Technology
3.1 | SFDC | Identify resolver ids with access to UAT | Dev Anand | 2021-01-15 | 2021-01-15 | 1h |  | Open
3.2 | SFDC | Create ticket to create / change resolver ids in UAT | Dev Anand | 2021-01-15 | 2021-01-15 | 1h |  | Open
3.3 | SFDC | Prep final code-base for UAT | Dev Anand | 2021-01-25 | 2021-01-25 | 0h |  | Open
3.4 | SFDC | Hand off final application run-book for admin/devops | Dev Anand | 2021-01-25 | 2021-01-25 | 0h |  | Open
3.5 | SFDC | Hand off code and configuration changes for deployment | Dev Anand | 2021-01-25 | 2021-01-25 | 0h |  | Open
4 |  | Test Readiness
4.1 | Test Case | Finalize test set - scenarios, test cases | Val Kilmer | 2021-01-11 | 2021-01-15 | 24h |  | Open
4.2 | Test Case | Ensure test cases are mapped to requirements | Val Kilmer | 2021-01-11 | 2021-01-15 | 4h |  | Open
4.3 | Test Case | Draw up test plan - test cases, dependencies, testers and testing dates | Val Kilmer | 2021-01-13 | 2021-01-20 | 24h |  | Open
4.4 | Test Case | Finalize test plan | Val Kilmer | 2021-01-21 | 2021-01-21 | 0h |  | Open
4.5 | Test Case | Communicate test plan to all stakeholders | Val Kilmer | 2021-01-21 | 2021-01-21 | 0h |  | Open
4.6 | Test Case | Import/create/update test plan in defect management tool | Val Kilmer | 2021-01-21 | 2021-01-27 | 8h |  | Open
4.7 | Test Case | Create tester and resolver ids in test management tool | Val Kilmer | 2021-01-28 | 2021-01-28 | 1h |  | Open
5 |  | Process Readiness
5.1 | Pre-requisites | Validate UAT entry criteria | Rama Man | 2021-01-25 | 2021-01-28 | 8h |  | Open
5.2 | Compliance | Create exceptions to access UAT data for developers/ testers | Rama Man | 2021-01-20 | 2021-01-22 | 1h |  | Open
6 |  | Deployment
6.1 | Deploy | Deploy code-base in UAT environment | John Op | 2021-01-25 | 2021-01-25 | 8h | 3.3 | Open
6.2 | Deploy | Apply configuration changes | John Op | 2021-01-25 | 2021-01-26 | 16h | 3.4 | Open
6.3 | Deploy | Create new users | John Op | 2021-01-25 | 2021-01-25 | 1h |  | Open
6.4 | Deploy | Change user emails in SFDC to identified user emails | John Op | 2021-01-25 | 2021-01-25 | 1h |  | Open
6.5 | Deploy | Set static passwords for identified users | John Op | 2021-01-25 | 2021-01-25 | 0h |  | Open
6.6 | Deploy | Provide permissions to identified users to "login as" different user | John Op | 2021-01-25 | 2021-01-25 | 0h |  | Open
6.7 | Deploy | Batch data changes | John Op | 2021-01-26 | 2021-01-28 | 24h |  | Open
6.8 | Deploy | Schedule or reschedule test-specific batch jobs | John Op | 2021-01-26 | 2021-01-26 | 2h |  | Open
6.9 | Deploy | Validation env - application | Val Kilmer | 2021-01-28 | 2021-01-29 | 16h |  | Open
6.10 | Deploy | Validate env - data | Val Kilmer | 2021-01-28 | 2021-01-29 | 16h |  | Open
6.11 | Deploy | Validate env - integration | Val Kilmer | 2021-01-28 | 2021-01-29 | 8h |  | Open
7 |  | UAT Prep End
7.1 | Plan | Flag UAT as ready for testing | Tom Ban | 2021-01-29 | 2021-01-29 | 1h | 5.1, 6 | Open